## Sheet1
Date | Start Time | End Time | Total | Activity | Notes
2021-11-04 | 13:40 | 15:00 | 1:20 | Code | Setting up SwiftUI Views.
| 20:30 | 22:30 | 2:00 | Code | Setting up SwiftUI Views.
2021-11-05 | 20:00 | 22:45 | 2:45 | Code | Creating the New Project view and adding to Constants
2021-11-06 | 8:30 | 10:00 | 1:30 | Research | Researching Realm database and MVVM for SwiftUI
| 10:10 | 11:45 | 1:35 | Code | Created reusable buttons.
| 11:45 | 12:45 | 1:00 | Research | Researching how view navigation and object lifecycles work in SwiftUI
| 13:00 | 15:00 | 2:00 | Code | Implementing NavigationStack and worked on navigating between RootView and NewProject view.
| 15:00 | 17:00 | 2:00 | Code | Still working on application state and view navigation.
| 20:15 | 23:15 | 3:00 | Code | Spent too much time trying to refactor data models to conform to Realm protocols only to figure out that I don't need them all to be stored in realm while mutating them live.
2021-11-07 | 13:50 | 18:37 | 4:47 | Code | Setting up the PlannedSprintView with its respective shared views to be part of the Roadmap view.
| 20:15 | 21:30 | 1:15 | Presentation | Working on Phase 3 Presentation
2021-11-08 | 20:15 | 22:53 | 2:38 | Code | Moved Settings into reusable view. Worked on enforcing validation when text is being input.
2021-11-09 | 21:00 | 22:49 | 1:49 | Code | Spent a bunch of time refactoring the Realm work I implemented because it was all wrong and wasn't able to get enums to properly get stored in a Realm db.
2021-11-10 | 8:30 | 11:49 | 3:19 | Code | Creating the project setup views and implementing the multi-date picker view
| 12:45 | 13:57 | 1:12 | Code | Simplifying data models and trying to hook up to Realm for db storage.
| 14:35 | 23:00 | 8:25 | Code | Hooking everything up and ensuring data validation is in place as well as proper navigation.
| 23:00 | 576:00 | 553:00 | Testing | Testing the application and resolving bugs found
2021-11-11 | 0:10 | 1:05 | 0:55 | Testing | Testing the application and resolving bugs found
| 8:15 | 8:45 | 0:30 | Presentation | Final presentation prep