## Sheet1
Date | Start Time | End Time | Total | Activity | Notes
2021-05-10 | 10:30 | 10:45 | 0:15 | Requirements | Initial project requirements gathering and research.
2021-06-07 | 20:00 | 20:45 | 0:45 | Vision Document | Creating the body and scaffolding of the Vision Document and filled out the Purpose and Motivation Section.
2021-08-09 | 21:00 | 21:45 | 0:45 | Feature Scope | Defining features and scope of application.
| 21:50 | 22:19 | 0:29 | Project Overview | Completing the Purpose and Motivation, Goals, and Risks sections of the Project Overview section of the Vision Document.
2021-08-23 | 10:00 | 10:50 | 0:50 | Vision Document | Worked on fucntional requirements section of Vision Document
2021-08-25 | 8:15 | 12:00 | 3:45 | Prototype | Setting up GitHub repo and initial project scaffolding.
| 13:30 | 16:00 | 2:30 | Prototype | Added data models and validation unit tests.
2021-08-26 | 16:30 | 17:00 | 0:30 | Meeting | Met with Professor Neilsen to discuss project progress.
2021-08-27 | 22:25 | 23:25 | 1:00 | Vision Document | Completing functional requirements section of Vision Document.
2021-09-01 | 10:55 | 11:51 | 0:56 | SQA Plan | Started work on Software Quality Assurance Plan Document.
2021-09-04 | 10:50 | 11:37 | 0:47 | SQA Plan | Completed work on Software Quality Assurance Plan Document.
2021-09-08 | 8:40 | 9:00 | 0:20 | Project Plan Document | Started work on Project Plan Document.
2021-09-13 | 21:00 | 22:00 | 1:00 | Project Plan Document | Filled out all sections of the Project Plan Document except the COCOMO Cost Estimate. Will complete this next session.
2021-09-16 | 20:30 | 21:00 | 0:30 | Repository Management | Uploading documents to the GitHub repo.
| 21:15 | 21:26 | 0:11 | Presentation Preparation | Prepairing for Phase 1 Presentation and sent out Doodle Poll to Supervisory Committee.
2021-09-17 | 20:01 | 20:56 | 0:55 | Project Plan Document | Gantt Chart work for Project Plan Document.
2021-09-20 | 20:30 | 21:50 | 1:20 | Prototype | Prototyping UI
2021-09-21 | 20:35 | 22:42 | 2:07 | Project Plan Document | COCOMO Model for Project Plan.
2021-09-27 | 8:40 | 11:05 | 2:25 | Phase 1 Presentation | Prepare Phase 1 Presentation.